## Sheet1
Tasks | Duration
Gather list of possible microprocessors | 1 Day
Collect data sheets on microprocessors | 1 Day
Select microprocessor | 1 Day
Order microprocessor | 1 Day
Discuss how to wire barcode reader to microprocessor | 2 Days
Create schematic for barcode reader wiring | 1 Day
Create prototype and debug | 3 Days
Create final model for barcode reader wiring | 3 Days
Create schematic for battery wiring | 1 Day
Create battery wiring prototype and debug | 3 Days
Create final model for battery wiring | 3 Days
Create final wiring model (may require use of eagle) | 1 Day
Order PCB (if necessary) | 5 Days
Brainstorm chasis options | 1 Day
Create prototype for chasis | 3 Days
Create final model for chasis | 3 Days
Create print chasis (if necessary) | 1 Day
Insert microprocessor into chasis and make adjustments | 1 Day
Add extra designs and features (if time permits)